## Tabelle1
QCM |  | DOMANI Quality Control Matrix
|  | 2024 |  | 2025 |  |  |  | 2026 |  |  |  | 2027
|  | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | M1-2 | M3-5 | M6-8 | M9-11 | M12-14 | M15-17 | M18-20 | M21-23 | M24-26 | M27-29 | M30-32 | M33-35 | M36
T1.1 | Day-to-day management, monitoring and reporting
T1.2 | Preparation and completion of the Consortium Agreement | 2024 Q1 M3-5: M4 – MS1
Done
T1.3 | Preparation of management guidelines | 2025 Q2 M6-8: M6 – D1.1
Done
T1.3 | Preparation of QA guidelines | 2025 Q2 M6-8: M6 – D1.1
Not available
T1.4 | Steering Committee work and Consortium Meetings | M2 – E1.1 Tartu | M5 – E1.2 online |  | M9 – E1.3 online | M12 – E1.4 Tallinn | M16 –E1.5 online | M20 –E1.6 online |  | M24 –E1.7 online | M28 –E1.8 Catania |  | M35 –E1.9 Ulaanbaatar
|  | Done | Done |  | Not clear | Done | Not clear
T1.5 | Quality assurance, certification, interactions of external QA officer | 2026 Q2 M18-20: M18 – EQA1; 2027 Q3 M33-35: M33 – EQA2
|  | Done |  |  | Not clear | Not clear | Not clear | Processing
T2.1 | Detailed survey of the capacities, curricula and provision | 2024 Q1 M3-5: M5-E2.2,E2.3
Done
T2.2 | Review of the EU’s and EU partners’ best practices to use as baseline | 2025 Q2 M6-8: M6 –D2.2 E2.1
Done
T2.3 | Development of DOMANI ToRs | 2025 Q2 M6-8: M6,D2.1, D2.2,MS2
Done
T3.1 | Organisational development for microcredential provision | 2025 Q3 M9-11: M10 –E3.1; 2026 Q3 M21-23: M22 –MS3,D3.1
Done
T3.2 | ICT arrangements for microcredential provision | 2026 Q3 M21-23: M21 - approved
T3.3 | Establishing the DOMANI mentorship program | 2025 Q3 M9-11: E3.4(1), E3.5 (1); 2025 Q4 M12-14: E3.4 (2), E3.5 (2); 2025 Q1 M15-17: M15 – D3.2
[5 empty] | Done | Done | Not clear
T3.4 | Capacity building for the development of microcredential provision | 2025 Q3 M9-11: M11 – D3.3,E3.2; 2025 Q4 M12-14: M12 – D3.4,E3.3
T4.1 | Development of amendments to national HE provision frameworks | 2027 Q2 M30-32: M30 - signed
T4.2 | Capacity building for the development of regulatory proposals | 2027 Q3 M33-35: M35 – MS4,D4.1
T4.3 | Development of competency fr. and microcredential course packages | 2025 Q4 M12-14: M12 – E3.3; 2026 Q1 M27-29: M28 – E4.1
Done
T5.1 | Development and updating of challenge-based modules | 2025 Q4 M12-14: M12 – D5.2 v1; 2026 Q4 M24-26: M24 – D5.1; 2027 Q2 M30-32: M30 – D5.2
Not clear
T5.2 | Development CLP DO-learn | 2025 Q4 M12-14: M12 - D5.2 approved
Not clear
T5.3 | Capacity building for the dev. of curriculum contents and e-learning | 2026 Q4 M24-26: MS5,D5.1
T5.4 | Capacity building for the development of curriculum contents and e-learning | 2025 Q3 M9-11: M10 –E5.1; 2025 Q4 M12-14: up to M12 –E5.2; 2025 Q1 M15-17: M17 – E5.3; 2026 Q3 M21-23: M23 - E5.4; 2026 Q4 M24-26: M24- D5.3,E5.5
[5 empty] | Not clear | Done, bad report | Done, bad report
T6.1 | Development and maintenance of the website, social networks and newsl. | 2024 Q1 M3-5: MS6,D6.1
|  |  | Done | Updated | Updated | Updated | Updated | Updated
T6.2 | Institutional multiplier events and exploitation of DOMANI deliverables | 2026 Q4 M24-26: M24 – E6.1,E6.2; 2027 Q3 M33-35: M35 – E6.3
T6.3 | DOMANI business-academia interface and the international conference | 2026 Q4 M24-26: 1-1 seminar; 2026 Q1 M27-29: 2-2 seminars; 2027 Q2 M30-32: 1-1 seminar; 2027 Q3 M33-35: M35 – D6.2,E6.4
T6.4 | Development of the sustainability and business plan | 2025 Q4 M12-14: M12 – D6.3 v1; 2027 Q2 M30-32: M32 – MS7,D6.3
Plan is not available
* Full descriotion of the tasks in the comments of the cells in column B
For each task in the matrix, there are cells for full description of the Deliverables, Milestones, Deadlines, etc. The full description, as well as Status and Evaluation of the task can be add in the comments